## System-PAPP Status
Status Name | Name | Description | Status Date | Status Comments | Start | End | Functional Area | Sponsors
Approved (Not Started) | ITPC-0632 Outsource University Check Printing | Solicit bids for the University of Illinois System to outsource check printing and distribution operations to a vendor with industry expertise, redundant failover processes, business continuity assurances, and high-speed operations that can fulfill University stakeholder requirements. Outsourcing approved check files to an external vendor for maximum operational performance, business continuity, and providing this critical, essential service will improve the highly manual process used today and better leverage industry expertise and maximize University resource allocation for responsibilities that increase value. • Anticipated cost savings or cost neutral from equipment needs, paper supplies, reduced staff time and effort, and postage costs. • Transfers risks for continued operations of critical services, and recovery activities for issues to the vendor. • Shifts costs and liability to the vendor for ensuring end to end reconciliations and accuracy to eliminate printing errors such as damaged checks, missing checks, or duplicate checks. |  | Status remains- Will hold off on starting effort until other potential projects scope/goals are defined to determine if there is need for this effort. | TBD | TBD | Finance | Bill Patterson, Gloria Keeley
Approved (Not Started) | ITPC-0679 New page for GAR customers to make updates in Banner | University of Illinois annually bills 6,700 departmental customers for over $71 million in non-student receivables through General Accounts Receivable (GAR). University Bursar is requesting creation of a new GAR customer page in Banner Self-Service (alternative detailed in Section 15) for the 3,000 monthly GAR customers that would help facilitate self-service account maintenance functions as well as allow University Bursar to leverage our online billing and payment portal. The new page would allow GAR customers to login, review, and update account demographics: email(s), address(s) and phone number(s) utilizing currently available Banner APIs; replacing manual account updates. Additionally, GAR customers would be able to access UI-Pay, the University of Illinois System billing and payment platform, UI-Pay, to view their current bill, historical bills, make payments, sign up for payment plans and view real-time account details. Benefits: Currently many processes with GAR customers are manual and require effort from both University Bursar and a University Departments to maintain the accounts as well as provide account services. The new GAR self-service page would allow the University to utilize Banner provided APIs to automate the collection and maintenance of email addresses and billing addresses as the customer would have the access to updated themselves. Additionally, gaining access to UI-Pay would give the customers more services than are currently available. The customer would be able to see real-time information versus one day old. They would gain access to historical statements which are currently not available online and are only paper copies. They would be able to sign up for customized payment plans. Last, they would have the option for additional ways of paying like international wires. These improvements would increase ease of use for billing departments, departmental customers as well as improve revenue recognition and the billing cycle. The University would also be able to decommission an internal GAR payment portal, which struggles with technical support and updates. This would also reduce compliance risk surrounding e-checks and credit cards payments. |  | Project approved by ITPC and awaiting resources and outcome of other in-progress Bursar projects to determine which next Bursar projects will start. | TBD | TBD | Finance | Muna Bist
Approved (Not Started) | ITPC-0680 Streamline State Offset Process with new tables & form | University Bursar is requesting a new Banner table(s) and user interface form for the State of Illinois Offset Process. State Offset is a process required by Illinois state law in which the delinquent accounts are submitted to the state for the purpose of collections. As a state agency the University of Illinois is required to submit claims to the state comptroller on delinquent accounts that meet the specified criteria of having balance of $500 or more that is past due more than 60 days. Section 10.05 of the State Comptroller Act (15 ILCS 405/10.05) requires the Comptroller to deduct from warrants payable to any person the amount for which there exists a claim due and payable in favor of the state. Prior to submission of the claim, a warning letter must be sent to the debtor outlining the planned action and their rights to dispute the debt. After the warning letter is sent the debtor has 30 days to dispute the debt and/or request a hearing on the validity of the debt. Following the 30-day period, Bursar submits any non-disputed accounts with the comptroller and performs monthly maintenance on those accounts to keep balances up to date. The new table(s) would house all the data that is created by the University for the offset process, such as letter date, dispute date, offset submit date and Deduction order number along with the data created by the comptroller, such as IW Number, claim status, and update date. The table(s) would be updated by consuming standard feeder files from both the comptroller and Bursar as well as being editable via a Banner screen. Bursar would then utilize the new table(s) and screen to streamline the process for both students and staff by being able to see data in real-time. Benefits: Will eliminate the lag time between process updates for accounts. Will be more accessible to employees who can instantly access updated account data. Will eliminate the risk bad data or losing account information due to human error. Will improve data reliability being reported for quarterly report on State Offset which is being used in legal and audit purpose. Will eliminate the need for a middleware database and process, and the staff time dedicated to maintenance and upkeep, by incorporating the business data in Banner. |  | Project approved by ITPC and awaiting resources and outcome of other in-progress Bursar projects to determine which next Bursar projects will start. | TBD | TBD | Finance | Muna Bist
Approved (Not Started) | ITPC-0684 Automate & track annual term-based detail codes process | University Bursar would like to automate our existing manual processing of Term-Based Details Codes. Each year, Bursar works with the 10 University departments to update the 650 term-based detail codes. The process is labor-intensive, using Banner screens to make copies of old records and then modify the records directly in Banner with details provided via email from the departments. Allowing for multiple points of user error. Additionally, departments will send the data to our office piecemeal leading to a long processing time. Additionally, we would like a BPI engagement to review the current process and determine the best direction forward. Benefits: Creating an online system for term-based detail code data to be processed through would allow for gathering concise term-based data up front, timely status feedback for requesting units, dashboard for each partnering unit to efficiently review term-based updates when it is their turn to review, streamlined C-FOAPAL interface with banner, automatic upload of a feeder, reduced manual errors, decrease overall timeline for all units involved. |  | Next on Bursar's priority list to start. | TBD | TBD | Finance | Muna Bist
Approved (Not Started) | ESGC-0727 Automation of the Canadian Tax Request Form via Self-Service Sponsors | University Bursar would like to automate our existing manual processing of the Canadian tax form requests via Banner Self-Service. Each year Bursar creates the Canadian TILLA forms for the Canadian students who request the Canadian tax forms. The process is labor-intensive manual work which requires using Banner screens to extract the payment and registration details of all the students who request one. The process in which we intake the student can request the form from Bursar is also makeshift form in webtools in which students enter the form and Bursar staff needs to manually extract and verify the requests on a frequent basis. This doesn't have a seamless standardized process like the 1098T for domestic students. Additionally, other departments like registrar are involved in creating in some of the forms which have created redundancy and the possibility of incorrect reporting on payments and registration details from two different sources. The manual process includes having to: * Receiving the request forms either via webtool or from direct emails either from students or other departments. * Create a pdf with the student information for the registered terms, calculating the credit hours for the tax year, verifying with the students about the specific territory related forms. * This form process, unlike 1098T, doesn't have a fixed time frame, so, the forms can be requested throughout the year. University Bursar would like to create a process that would streamline the process via banner self-service by creating two different Canadian tax forms pdfs that can be filled with the information University provide whenever a student would like to access one. Benefits: Reduce manual errors and redundancy / Reduce the wait time for the student / Secure delivery system for the tax related documents of the students |  | XFG has approved this project and is ready to start when other higher priority Bursar projects complete. Need to determine the start date and resource needs. | TBD | TBD | Finance | Joe Shroyer
Approved (Not Started) | ITPC-0707 Integration strategy with iBuy & relevant dept systems | The university has been focused on making iBuy the centralized purchasing tool for the system. As we have gone through this process to integrate iBuy to Banner, we have identified shadow systems that are used for purchasing, accounting, and receiving. Upon further investigation, the use of shadow systems in conjunction with iBuy creates manual work for the related departments. By integrating these solutions, we plan to remove these manual efforts. We will conduct a proof-of-concept (POC) for this integration using two departments and two different shadow systems to verify this can be successful. We have selected Facilities Services at UIUC (F&S) and the Illini Union Bookstore and Retail Operations at UIUC to test the integration. The goal will be that the development work can be re-used for future areas interested in the integration to remove manual work. Expected Benefits: Eliminating significant time manually entering requisitions, purchase orders, and invoice data in respective systems. Improve data accuracy by leveraging electronic data vs. manually entered information. |  | Status remains- Awaiting the implementation of digital mailroom. | August 2024 | March 2026 | Finance | Aaron Carter, Kelly Block, Maria Thompson, Tod Petrie, Brad Trankina
On Hold | SYS-0026 Implement Policy Database Software | In project SYS-0025 Research Policy Database Tools Research, we investigated available tools and systems to create a centralized database for all policies. We reviewed products from four different vendors and evaluated TeamDynamix and the KnowledgeBase as potential solutions. Onspring was the vendor selected, and we are now ready for purchasing and implementation. System Offices Shared Services (SOSS) and the Business and Finance Policy Office (Policy) will work with System Purchasing and Support Services to procure Onspring, and then work with AITS to configure the system. As part of this project, we will also formalize support for Onspring, which will be a shared responsibility between SOSS and Policy. | 2026-01-06 11:06 | We are still waiting for the contract to be signed. We are currently working on developing a policy template. | February 2025 | June 2026 | Other | Karen Greenwalt
In Process | ITPC-0708 Capital Programs’ Kahua Application Integrations and Reporting | The University Office of Capital Programs (UOCP) has been in the process of implementing Kahua to replace two software systems that currently provide project and financial management support to university capital construction units. This effort will implement reporting and needed integrations that were not able to be included in the initial July 2024 planned release. This is due to an accelerated timeline and functionality that was not determined to be available as we are implementing the Kahua product that will try to be addressed with a few focus areas in this project, if prioritized as such. Reporting functionality needs that are in place with PRZM and FCPWeb through the EDW will now need to come from Kahua. Establishing the connection and design of the new reporting tables/universe in the EDW are part of this project. Expected Benefits: Reduce or eliminate duplicative data entry ¦ Provide a more modern and streamlined technological solutions to common project management issues ¦ Allow for better reporting to be used or shared to manage all capital projects | 2026-01-08 09:23 | Reporting - We continue to work thru data sourcing analysis. Once complete, will move into data modelling and development. We have a ticket open with Kahua regarding KBuilder and waiting on response to address some technical issues regarding report creation. Integrations/Encumbrances - We are working on sharing findings and gathering input from the 3 universities on encumbrance handling. | January 2025 | June 2026 | Capital Programs | Nyle Bolliger, Mike Wilson
In Process | ITPC-0699 Update BO universes to new format to continue support | SAP Business Objects is the supported enterprise reporting tool used at the University of Illinois. Business Objects Universes are used to deliver standard reports and ad-hoc reporting capabilities. SAP has deployed a new format, UNX, for the development of the BO Universes. SAP has developed plans to deprecate the legacy format, UNV. In order to be able to stay on supported versions of SAP Business Objects, all BO Universes have adhere to the new UNX format. The proposed timeline for deprecation by SAP is to end mainstream maintenance December 31, 2024. Before that date AITS will have upgraded to SAP Business Objects BI 2025. | 2026-01-07 12:01 | Phases 1-11 of the universe conversions have been completed. Phase 12 and 13 are in progress. The team has identified universes for conversion for phases 14-20, and we will finish the universe scheduling once we reach Phase 15. The team has finished the final report repoints for phases 1-6 and are finalizing phases 7-11. Hiding identified unused reports is on hold until after the new year. The identified Unbound reports will be dealt with as the associated universes are migrated to avoid any unnecessary doubled work in this area. Partnered with the SOSS Change Management Team for documentation and communications for all impacted users. | October 2023 | September 2026 | DMA | Dimuthu Tilakaratne, Mike Wonderlich
In Process | ITPC-0719 Degree Planning Portal utilizing curricular analytics (Phase 1) | The Degree Planning Portal will be a statewide tool to assist prospective students looking to transfer from academic institutions across Illinois to the University of Illinois Chicago (UIC). The portal will help transfer students from community colleges map out semester-by-semester pathways to degrees. It will also benefit high school and first-year students by allowing them to map out their degree pathways. This portal will integrate curricular analytics and degree audits to create a personalized, term-by-term degree map toward timely graduation. This map will then guide transfer and first-year students through their academic journey, helping them to understand all requirements for their desired baccalaureate degree program. Accessible via a website, the portal will provide information on the transferability of course credits from community colleges or high schools, thus maximizing the chances of completing an academic program in the minimum number of terms with minimal credit loss. Implementation of this tool will be a multi-phase effort, with the scope of the current phase (Phase 1) data extraction and development of the application front-end for students at UIC. This project will also prepare a plan for phase 2 of how to expand to the other universities in the system. Expected Benefits: Assist in the student onboarding process / Provide a clear plan and schedule to best achieve a degree in the student's desired program | 2026-01-07 12:06 | At this time, Nikos has identified concerning behaviors and engagement from the Damour team/vendor. Due to this, the internal teams have decided to move forward with “Plan B”. “Plan B” is that we are moving forward with development activities essentially sidelining Damour in favor of utilizing Internal (UIC, System Office, UIUC) resources instead. Half Day working session on 1/7 completed successfully, focusing on initial designing, solutioning and strategic planning. Next steps have been identified for internal development, and we have the first discussion setup with DegreeSight as a potential vendor partner on 1/12. | November 2024 | April 2026 | DMA | Nikos Varelas, Amy Knetl, Nick Jones
In Process | ITPC-0677 Improve Sharing & Collaboration with Data Lake Services | This project will implement an enterprise data lake service for use by data analysts. The effect is that data analysts will have a centralized data storage service that they can utilize instead of having to maintain or procure their own. The Microsoft Azure data storage solution will be used as the tool upon which the data lake service will be constructed. Processes and procedures to establish, maintain, and support the service will be defined during this effort. This includes governance, access and security, training, and support. Benefits: An enterprise data lake provides for better sharing and collaboration with data. Data analysts can store data in the data lake and utilize that data for analytics and reporting. This provides data analysts with the next generation data analytics capabilities necessary to provide the necessary information to University decision makers. Actionable insights available through better sharing and collaboration allow for better, informed decision making. | 2026-01-07 12:02 | Working on creating additional documentation for Data Lakes and Early Adopters. We still need additional research/analysis about what learning & KB articles to create. Campus Areas are working on multi-tenant solutions, next working session set for 1/13. Potential early adopter groups we talked with include: Grainger College of Engineering – UIUC (Pooja Yadav, Sarvani Putta, and Ben Kaap), Office of Institutional Research – UIC (Thomas Warfield), Student Affairs Technology – UIUC (Nate Britton, Nate Baxley), Office of Vice Chancellor for Research – UIC (Bhavin Patel, Miguel Martin, Chainanya Gokhale, Shreys Kulkarni, Nishant Agrawal), Office of Medicaid Innovation Data Lake Discussion. Team is working to prepare a demo on data fabric for potential early adopters (Education Piece). We will proceed with setting up early adopters in the respective tenants so that they can begin building and setting up the Data Lakes, and the Early Adopters are preparing full use cases for review. Working on additional Data Lake Security Documentation for the ESA teams. | July 2023 | April 2026 | DMA | Dimuthu Tilakaratne
In Process | ITPC-0645 Deliver improved financial data with FPPM Dashboard | The FPPM Dashboard will deliver improved financial information insight across the University of Illinois System. It will be used by University leadership, Budget Officers, Deans, Directors, Department Heads, Academic Fiscal Officers and Business Managers to monitor their financial process performance health in an informative and customizable format divided by actionable and informative items. The Dashboard will also be used by the CFO and system office staff to monitor the efficiency and effectiveness of financial processes and to offer support needs based on institutional risk. Dr. Ghosh has met with the project sponsors to confirm his support to offer financial process performance information in this format. The current iteration includes five metrics of actionable information and the Analysis team will interview key personnel in units, colleges, universities, and system offices to determine additional metrics and style options. The Dashboard and metrics were preliminarily vetted through various business staff to confirm both efficacy and value. Expected Benefits: By defining financial parameters and the data elements needed from disparate systems to appropriately measure financial process performance, day-to-day operations will be more focused efficient and effective. The Dashboard will enable the unit and college leadership to collaborate with system office staff in defining the data, access, and other Dashboard requirements so the product applies common definitions to parameters and improves process transparency. The Dashboard will highlight problematic process areas so education and resources may be applied which will in turn reduce state compliance audit findings. Additionally, savings will be realized as staff resources allocated to monitoring financial operations will become more efficient and will allow for resources to be used elsewhere. | 2026-01-05 11:53 | This project will be completed by implementing multiple iterations of the Finance Process Performance Measures dashboard. The dashboard is embedded in My-UI-Financials application. The second iteration is in prototype testing with the sponsor group to make sure the calculation logic is correct. Another visualization may be added before starting User Acceptance Testing in the My-UI-Financial application. Scope for iteration 3 has been defined. | August 2022 | December 2026 | Finance | Kelly Block, Brent Rasmus
In Process | ITPC-0682 Automate SAR bill format to reduce Bursar process time | University Bursar is requesting a new process to be built to create the monthly bill file submitted to our vendor NBS Quikpay. University Bursar is responsible for the monthly student billing of our 95,000 students. We utilize the built-in banner billing process, TSRRBIL, which uses the banner data to create the monthly billing statements for the students. This process then outputs a flat file that is uploaded to NBS QuikPay server for them to render the bills for the students. The process had previously been automatic with AITS running the process, encrypting the file and uploading to NBS Server. In recent years, the process has become manual as the baseline banner file contains errors. These errors stem from the banner data containing tab characters, multiple rows of city/Zip code, foreign characters, etc. The file now has to be manually reviewed each month to remove the issues before submitting to NBS. This has proved to be an obstacle in having an efficient billing process since the bill load process may sometime take multiple attempts when there is manual review of the flat file. To eliminate this billing process delay, the bill file needs to be reformatted in a Nelnet server acceptable format which won’t be rejected during the upload process. In addition, University Bursar wants to take this opportunity to improve a few other issues that have hindered the efficiency of billing. Specifically, NBS now allows for schools to send over the student email address as part of the bill file. This was eliminating a custom step that Bursar performs each month to obtain the email addresses of students not within NBS system and send a manual email blast. Therefore, University Bursar is looking to change the bill specs with additional information as well as build a customized parser that would clean the existing data fields being retrieved from the Banner for special characters and have them in appropriate format before uploading the file to the Nelnet server. This project would have a number of Benefits for Bursar and Students: Will help eliminate the upload failures to the Nelnet server. Will create an efficient monthly billing process by cutting down the processing time to one day instead of taking up to four days. Will automate the bill notifications to all come from NBS instead of a separate manual process from Bursar. | 2026-01-08 08:23 | Changed Percent Complete from 25% to 29%. Development continues for SAR bill formatting. We are reviewing the DAT files that have been created thus far. In reviewing those files, we found some discrepancies that we are waiting on Nelnet for confirmation if a different header can be created. If not, we may need to change section names to fit their formatting. | March 2025 | April 2026 | Finance | Muna Bist
In Process | ITPC-0593-E S2P Card Program Project | As Jaggaer does not offer a credit card purchase and payment mechanism, this effort is outside the scope of the iBuy Optimization. It is strategically important to assess the advantages and disadvantages of various card programs. It is also vital to identify an alternate solution to the existing PCard software which is at end of life. This request is for approval to complete the following: • Create a team to analyze the various uses of credit cards available as possible solutions to a variety of procure to pay needs • Investigate how credit card uses align with procurement strategy and the cost/benefit of deployment of the various identified possibilities. The team will consider cost savings due to reduced transaction costs as well as the ability to leverage the income that can be generated as the result of robust | 2026-01-08 08:18 | Card Services suggested a go-live date in Mid-March. Comms are being created to communicate the upcoming changes to the larger community. We are working with Bank of America to resolve some reporting issues with the HR Work integration. New Go Live date is being discussed, possibly targeting the week of 3/17. | January 2024 | March 2026 | Finance | James Martinie, Darren Strater
In Process | SYS-0027 iBuy Training Program​ | Based on recommendations from University Audits and in keeping with requirements already in place for Card Services, Journal Vouchers, and FABweb/Biennial, this project will create required training that must be completed prior to receiving Requestor or Approver access in iBuy. Introductory course(s) will be created and accessed through Ability LMS for Requestor and Approver profiles and the Security Application will be configured to query the Ability LMS tables for course completion when provisioning access for iBuy Requestor or iBuy Approver. Additionally, an ongoing training program will be developed to support iBuy users and help ensure they are following all applicable policies, procedures, and best practices. | 2026-01-14 10:34 | Changed Percent Complete from 50% to 66%. We are putting the final touches on the Intro to iBuy course and plan to send out this week for review by the Customer Advisory Group and also for accessibility. We are on target to release the course in early February. | May 2025 | February 2026 | Finance | Brad Henson, Justin Johnston, Aaron Rosenthal​
In Process | ITPC-0674 HR/UPB updates due to new SURS Pension Admin System | SURS will be transitioning to a new Pension Administration System in the next 4 years. This will require significant modifications to existing business processes and systems. Human Resources (HR) and University Payroll & Benefits (UPB) will need to analyze current business processes, determine how they need modified and implement new policies and procedures to accommodate the new system. AITS will need to modify existing applications, files and reports for the various SURS components that exist today. In addition, there will be a need for new applications, files, and reports to meet the needs of the new SURS Pension Administration System. Expected Benefits: Faculty will have accurate reporting of SURS eligibility and benefits to SURS / Meet the requirements of the new system | 2026-01-02 14:17 | Worked has stopped on this for now due to higher priority projects and production issues. This work should pick back up by the end of January | March 2023 | October 2028 | HR | Jami Painter, Cheri Canfield , Shari Mickey-Boggs, Melissa Mlynski, Larry Hanyzewski
In Process | ESGC-0723 Purchase, Analyze and Implement Ellucian Intelligent Learning Platform | As we move towards a SaaS environment, we would like to continue taking advantage of the products and applications offered by Ellucian (our current ERP vendor.) In February 2024, we implemented Ellucian Experience. This is the platform that Ellucian is using to launch all of its new technology. We initially used it as a platform for entry into our Banner Self-Service applications, but there is untapped potential with Experience. One of the additional products being introduced by Ellucian is the Intelligent Learning Platform (ILP). This uses Experience to integrate the University’s Learning Management Systems (Blackboard for Chicago and Canvas for Urbana and Springfield) with Banner. | 2026-01-07 09:43 | Name Type Handling for PPN: Filed a ticket with Ellucian to clarify the use of favored, preferred, and legal name types in Ethos and ILP, and determine any implications for mapping PPN to favored name. ILP/Banner Grading Issue: Investigating to resolve the issue where grading for modes other than credit/no credit (e.g., A or V grade modes) is not working properly in Canvas/Banner integration. ILP Configuration Change Process: Will Schedule and conduct a TAM student meeting to define and document a process for handling ILP configuration changes, including tracking requests, approvals, and implementation details. As part of the ILP project, we implemented a process that populates the gobtpac_external_user field in Banner with the user’s NetID and ensures it is maintained going forward, enabling ILP to use this value for the LMS (Canvas). This was accomplished using the third-party-access-audit-pin-history API with PUT requests, which update existing gobtpac records or create new ones when necessary. UIC Spring 2026 Pilot: Reviewed pilot status; confirmed current setup remains in place. Testing to complete this week for start of term. UIS -Testing of 2026 Spring Semester in TEST environment November 6th complete. UIS confident in testing and will reconvene with AITS in March 2026 to continue. UIUC - Set up and testing continues in the test environment. | April 2025 | November 2027 | Student | Nyle Bolliger, Rod Hoewing, Drew MacGregor, Shannon Dwyer, Szymon Machajewski, Brian Catherwood, Kara McElwrath
In Process | ESGC-0725 Vended Application Testing and Remediation for ADA Title II Regulation Updates | The Department of Education has issued web accessibility regulations pursuant to Section 504 of the Rehabilitation Act, which prohibits discrimination in all public and private programs receiving federal financial assistance. This project will bring highly used AITS-developed applications into compliance with Federal Title II regulations. This project will bring AITS-supported vended applications into compliance with Federal Title II regulations. Expected Benefits: Ensure AITS-maintained vended applications compliant with the updated mandate / Improve accessibility of AITS-maintained vended applications for our faculty, staff, and students | 2025-12-10 09:42 | Changed Percent Complete from 38% to 40%. We have sent letters to all known emails with vendors and will work to contact the remaining few through customer portals. We will continue meeting with product managers to review their next steps in the Vendor Accessibility Process Document. The first vended product has also started the escalation process - the SOARC committee will provide more recommendations and next steps to help us validate and update our process. AITS product liaisons can submit tickets for testing vended apps with or without a VPAT, those with VPATs will be given priority as well as those identified as having a higher user base. | February 2025 | December 2029 | Technology | Nyle Bolliger; Jane Stone
In Process | ESGC-0744 ​SiteMinder Retirement​ | The purpose of the SiteMinder Service Retirement is to improve and consolidate the user authentication experience while eliminating redundant services. The goals of this project are to Migrate authentication for all AITS web applications from SiteMinder to use Campus IDPs, Migrate authentication for all remaining campus clients of SiteMinder to use Campus IDPs and retire the SiteMinder Service. The Benefits of this, are the Improvement to the SSO experience for our users, eliminating an authentication service that is 95% redundant with authentication services provided by campuses, Saving licensing cost of SiteMinder (~$100K annually), Saving operational support time and furthering our overall goal to get to Passwordless Authentication. | 2025-12-10 07:28 | Working through the 4th IDP/discovery service as the planned temporary solution for the SiteMinder replacement while continuing coversations about the long-term plan for campus authentication as it relates to IAM strategies and efforts. | July 2025 | January 2027 | Technology | Peter Herrig, Brian Schoudel​
In Process | ESGC-0745 ​SitePublish Replacement Project​ | There are security concerns with SitePublish. There have been multiple serious security incidents with the current CMS system hosted on AITS infrastructure. The first incident occurred In December 2019 when attackers hacked into the CMS system. The SitePublish CMS shares infrastructure with other enterprise systems including Banner, so our most critical systems were at risk. The vulnerabilities concern a third-party plugin, Telerik, which is required by the SitePublish CMS. Because it is a third-party dependency, AITS cannot update the Telerik module directly to respond to new threats. New versions of the SitePublish software have been slow to be released. Several reviews with Security Officers among System Offices and Tech Services were conducted and mitigation strategies were put in place. However, additional incidents have occurred since 2019, and additional mitigation strategies have been implemented. We are currently blocking the Telerik plugin with a few exceptions where we allow certain Telerik functionality restricted via VPN for features which are required and have no alternative. Along with this the vendor has recently confirmed that the version of SitePublish used by AITS will be sunset – no future versions of SitePublish will be released. An analysis project was conducted with the help of CDW to complete a review of the current situation and recommend potential alternative solutions for website hosting within an external/cloud hosting environment. After narrowing down our list of potential vendors, we spoke to the we were interested in, received demos, compared and contrasted each before ultimately deciding on Squiz. We are working through contract details with the newly selected system. Squiz will help with the implementation project in coordination with System Office Shared Services (SOSS) as well as AITS to move all sites from SitePublish to Squiz. | 2025-12-10 15:46 | Changed Percent Complete from 20% to 35%. Each of the 2-hour Discovery Sessions have been completed. We are currently working with the vendor to review and approve work tickets as they are created. Once the Discovery phase is complete, a development plan and timeline will be created. Our hope is we will be able to migrate all sites by May or June and be able to avoid the need to renew our SitePublish license on July 1st | August 2025 | June 2026 | Technology | Nyle Bolliger, System Office Shared Services (SOSS)​
In Process | ESGC-0747 Multi-Factor Authentication Switch Over (Duo to Microsoft Entra MFA)​ | Based on the Multi-Factor Analysis Project and output analysis recommendation, The decision was made to switch from utilizing Duo for our MFA to Microsoft Entra MFA. During this transition, Duo will be renewed to offset some of the known user impacts to certain applications that Microsoft does not currently integrate with; with the overall goal being total transition to Microsoft Entra MFA. This is due several factors outlined in the analysis recommendation, one of the main reasons being that the Duo MFA cost per user is much higher when compared to Microsoft Entra MFA, which is included with many of the contracts and agreements already in place with the Campus systems. Below is the set of project goals that are required for the switch over to Microsoft MFA. 1. Implement EAM in Entra 2. Acquire Licensing for Affiliates 3. Minimize Duo Deployment 4. Align Authentication Deployments 5. Formalize Option to Opt-in to Microsoft Entra (Voluntary Opt-In Option) 6. Identify Duo Edge Cases 7. Radius Server Builds For non-web Duo 8. Consolidate Log data/Enrollment data for MFA with Data Lakes | 2026-01-07 12:10 | Changed Percent Complete from 1% to 5%. Initial project kickoff/planning meeting is scheduled for 1/8/26, focusing on creating the best estimated timeline while identifying resource needs as well as parallel activity tracks. Currently working on resolving a known licensing issue for MFA that the SiteMinder Project is already running into and discussing planning around User reduction and removal during the weekly MFA meetings. The other MFA projects (SMS Phase Out, SiteMinder Retirement, SiteMinder Retirement) all have dependencies/tie into the MFA password-less goal of this project. | November 2025 | January 2027 | Technology | Jeff Domeyer, Joe Barnes​
In Process | ITPC-0620 Replace SecApp to improve access request / provisioning | This project’s purpose is to build, integrate, and deploy an AITS Security Application to replace the existing, homegrown product that has reached its limits of effectiveness and adoption at the University. The AITS ITPC-0584 Security Application Analysis project team completed a full examination of the current process and wrote user stories with requirements that aided in evaluation of a build or buy (vended) solution recommendation. The overall final recommendation to the University of Illinois AITS Leadership was to utilize the existing midPoint application architecture as a backend to meet the existing business needs and allow for additional functionality and future growth. Additionally, the recommendation included creating a governance structure and establishing standard processes for integration and adoption post-implementation as well as develop a training plan to assist in adoption of the new product. | 2026-01-08 10:44 | Access Management Enhancements * Improved USC workflows for Add/Edit Access. * Added validation for duplicate settings and historical data entry. Profile Configuration * Completed setup for more Banner Finance, Salary Planner, and EPAF profiles. UI/UX Improvements * Enhanced navigation indicators. * Updated error messages and usability for historical VPD settings. Documentation & Analysis * Conducted analysis for My UI Financials integration with Data Warehouse. | August 2021 | March 2028 | Technology | Kelly Block, Karen McFarlin
In Process | SYS-0022 Analysis of potential Banking Disbursement Services RFP | Our current bank is BNY Mellon. We have been with them since 2006. Senior management has determined it to be beneficial to consider changing the incumbent bank, and review and evaluate alternative solutions and products that are available in the market. The primary goals of this effort are to solicit proposals relating to banking services for the following disbursement activities: University Payroll account to disburse payroll direct deposit (ACH) to university employees at all locations. University Payables disbursement account for general disbursement activity for the University including check, ACH. Student Refunds account to make ACH payments for student financial aid refunds. Funding account to facilitate the daily funding of disbursement activity for the accounts referenced above. Review and evaluate new services and products vendors may have to offer to improve efficiencies and operations of the System. Once it is determined what services a new banking service can offer based on the RFP output, we will decide what current processes could be impacted and what services we will be requesting from that new banking service. An implementation proposal will be submitted to PAPP and ITPC for the implementation of the new banking service as well as any new services or adjustments to current processes. | 2025-12-10 15:39 | Final updates to the requirements document have been made and handed over to System Purchasing. They are working to incorporate these into an RFP template and we hope to be able to put it out later this month. We are also putting together representatives from each area that will be part of the evaluation group. | February 2023 | February 2026 | Treasury | Nichole Roberts, Sarah Crane
Completed | SYS-0021 Facility Condition Assessment Investigation | The University of Illinois Urbana-Champaign (UIUC), the University of Illinois Chicago (UIC), and the University of Illinois Springfield (UIS) seek to embark on a system wide facility condition assessment (FCA). The FCA will provide a comprehensive evaluation of building systems, identify deficiencies and suggest and prioritize future repair or replacement needs. Building surveys will evaluate the general health of physical facilities by identifying and arranging inadequacies that require critical, urgent, and necessary remediation in alignment with risks associated with the inadequacies and their potential impact on life safety, continued building operation, and functionality. The appraisal will consider the age and serviceability of systems, components, and finishes of buildings to forecast replacement of facility assets as they reach the end of their serviceable life, as well as regular preventative maintenance impacts on expected replacement timelines. The objective of this investigation effort is to issue an RFP and based on responses determine next steps with the goal to identify a consultant to assist with the analysis and provide expertise on a software solution to track asset improvements and up-to-date condition reports. | 2026-01-20 13:37 | Changed Status from In Process to Completed. Changed Health from Green to None. Changed Percent Complete from 95% to 100%. The assessment findings are complete, and the related data is accessible to all universities. While we do not yet have the final report from the vendor, it is a formality and we are likely to manage any communications about the assessment findings internally instead of relying on the report to convey information to leadership. | September 2022 | December 2025 | Capital Programs | Mike Wilson
Completed | ITPC-0593-A S2P iBuy Optimization Project | Optimize the Jaggaer eProcurement module by taking advantage of functionality that has not been fully implemented, which may involve undoing system workarounds which were created by the University when the iBuy system was originally deployed. The eProcurement module incorporates requisition, catalog, and spend tracking functionality that should be leveraged. Work with Jaggaer and Ellucian to resolve issues related to the current integration method. Determine where the University may have deviated from Jaggaer’s standard configuration to facilitate upgrades, bug fixes, and ongoing maintenance. | 2026-01-14 15:49 | Changed Status from In Process to Completed. Changed Percent Complete from 85% to 100%. Closing project in TDX as of 1/14/26. | July 2019 | January 2026 | Finance | Gloria Keeley Michael Bass Dr. Ghosh Janet Parker Jerry Joseph Mike DeLorenzo Brent Rasmus Kelly B
Completed | ITPC-0681 Automate billing process with new GAR Bill Banner table | University of Illinois produces over 37,000 GAR bills for 6,700 departmental customers for over $71 million each year. University Bursar is requesting a new Banner table to be built that would be populated by the Monthly GAR process, TFRBILL. The new table would allow Bursar to fully automate the billing process by containing all of the billing data inside Banner instead of just in a Banner lis file. The process and table would be a copy of the current setup utilized by the Monthly SAR bill process, TSRRBIL. The new table would be populated each month upon the TFRBILL process run and contain all appropriate data from the bill run, such as bill date, due date, statement number, address type and sequence number, total account balance, and total past due amount. Currently details of GAR bills are maintained only in the standard Banner lis files and pdf output of the process. Benefits: With a static bill table, Bursar can streamline processes related to the printing process of the GAR bills, being able to query addresses in realtime and create an automatic process to send files to print services based on addresses saving Bursar over 100 hours a year. Additionally, Bursar would be able to produce historical reports directly from Banner reporting sources such as REPTPROD. The table would help Bursar to research any questions related to GAR billing from a central location versus digging through Banner lis files. Last, The table would be a new resource for University departments to be able to review data provided to there customers through Banner GAR. | 2025-07-31 10:54 | Changed Status from In Process to Completed. Project is completed and closed. | May 2024 | July 2025 | Finance | Muna Bist
Completed | SYS-0024 Motor Vehicle Record (MVR) Ordering Process | The System needs to implement a process for ordering MVRs for “regular drivers” of university owned/leased vehicles. This is due to a new underwriting requirement from the System’s Excess Liability insurance carrier. The project includes determining the university’s definition of regular driver, identification of a method (vendor) for ordering the mvrs, procedure for reviewing mvrs, potential storing of PII, and development of process/policy for how adverse mvrs will be handled. | 2026-01-20 13:33 | Changed Status from In Process to Completed. Changed Health from Green to None. Changed Percent Complete from 85% to 100%. The Motor Vehicle Report Policy went into effect on 12/18/2025 and MVRs are being ordered according to policy. | June 2024 | December 2025 | Other | Tina Harlan, Shelly Romack
Completed | ITPC-0605 Impl ITSM(IT Svc Mgt) and PPM(Proj Mgt) Cloud Solution | This project is to purchase, integrate, and deploy an enterprise ITSM and PPM Software as a Service (SaaS) private cloud solution to replace the existing, vended on-premise product that has reached its limits of effectiveness and adoption at the University. The ITSM Research Group, formed by the U of I IT Leadership Team, built criteria to analyze and evaluate vended solutions that could meet the University’s business needs and replace the existing solution. The ITSM Research Group provided a gap analysis, decision criteria evaluation, and overall final recommendation to the U of I IT Leadership Team that pointed to TeamDynamix as the selected vendor to meet existing business needs and allow for additional functionality and future growth. | 2025-09-17 22:24 | Changed Status from In Process to Completed. Changed Health from Green to None. This project has completed in FY 26 | October 2019 | September 2025 | Technology | Kelly Block, Cynthia Herrera Lindstrom,Tulio Llosa, Greg Gulick